## BeastRise To-Do
🦁 ZVELT — TO-DO LIST COMPLET
Plan de lucru · filtreaza dupa Status / Prioritate / Responsabil · Dependente = ce trebuie gata inainte
# | Task | Descriere | Status | Prio | Efort | Ver. | Dependente | In progres de | ✓ Done
🔐 Auth & Onboarding
1 | Email/password auth | Signup, login, logout, JWT + refresh automat | Done | P0 |  | V1 | — | —
2 | Google Sign-In | OAuth flow + token storage | Done | P0 |  | V1 | — | —
3 | Onboarding flow | Start → concept → avatar intro → select → confirm | Done | P0 |  | V1 | Auth | —
4 | Avatar system upgrade | Design mai simplu, Apple-style, mai multe optiuni | Partial | P1 | 1z | V1 | Onboarding flow · Logo final | —
👤 Profile
5 | getMe complet | GET /v1/me - toate datele profilului | Done | P0 |  | V1 | Auth | —
6 | Update profil | PATCH /v1/me/profile — fix bug cheie bodweightKg | Partial | P0 | 0.5z | V1 | getMe complet | —
7 | Stats view in profil | XP, rank, streak, numar workouts, greutate | Todo | P1 | 1z | V1 | Update profil · Rank overall · Streak gym | —
8 | Setari cont | Notificari, privacy, unitati masura, deconectare | Todo | P2 | 1z | V1 | getMe complet | —
🏋 Workouts
9 | Lista workouts trecute | GET /v1/workouts — functional | Done | P0 |  | V1 | Auth | —
10 | Start + track workout | POST, tracker screen, complete flow + XP screen | Done | P0 |  | V1 | Lista workouts · Exercise library | —
11 | Workout suggestion AI | Sugestie din profil + creare din sugestie | Done | P1 |  | V1 | Update profil · Exercise library | —
12 | Exercise library | Lista exercitii + filtre + custom exercises | Done | P0 |  | V1 | Auth | —
13 | Muscle map upgrade | Heatmap intensitate front+back, interactiv | Todo | P1 | 3z | V1 | Start + track workout | —
14 | Streak gym | Backend exista, UI streak vizibil in profil | Partial | P1 | 0.5z | V1 | Start + track workout · Stats view | —
15 | Streak cardio | Streak separat pentru run/bike/swim | Todo | P2 | 1z | V1 | Log manual cardio · Streak gym | —
📅 Calendar & Activitati
16 | Backend history endpoint | GET /v1/activities?month= pentru zile cu activitate | Todo | P1 | 1z | V1 | Start + track workout | —
17 | Iconite activitate | Gym, run, bike, swim — set iconite consistente | Todo | P1 | 0.5z | V1 | Logo final (style guide) | —
18 | Activity calendar | Calendar lunar cu iconite mini per tip activitate | Todo | P1 | 3z | V1 | Backend history endpoint · Iconite | —
19 | Log manual cardio | Log run/bike/swim fara GPS (distanta, timp, calorii) | Todo | P2 | 2z | V1 | Activity calendar | —
🗺 GPS Maps & Tracking
20 | GPS tracking in-app | flutter_map + geolocator — traseu run/bike in timp real | Todo | P1 | 4z | V1 | Log manual cardio · Activity calendar | —
21 | Statistici activitate | Distanta, timp, viteza medie, calorii, altitudine | Todo | P1 | 2z | V1 | GPS tracking in-app | —
22 | Temperature API | Weather API (OpenWeather) pentru temp curenta | Todo | P2 | 1z | V1 | — (independent) | —
23 | Social overlay card | Card postabil: track + icon + distanta + timp + temp | Todo | P1 | 3z | V1 | GPS tracking · Statistici · Temperature API | —
24 | Heart rate pe overlay | Heart rate din wearable sau manual pe card | Todo | P2 | 1z | V1 | Social overlay card · Heart rate sync | —
25 | Export card ca imagine | Screenshot widget + share ca poza pe Instagram/Story | Todo | P1 | 1z | V1 | Social overlay card | —
🤖 AI Chat (DeepSeek)
26 | Integrare DeepSeek API | Backend endpoint /v1/ai/chat cu limita caractere | Todo | P1 | 2z | V1 | Auth · Backend running | —
27 | Caching raspunsuri | Redis/DB cache — acelasi raspuns pt intrebari similare | Todo | P1 | 2z | V1 | Integrare DeepSeek API | —
28 | Tips nutritie | Raspunsuri personalizate bazate pe profil + macros | Todo | P1 | 1z | V1 | Integrare DeepSeek API · Nutritie UI | —
29 | Tips exercitii | Sugestii exercitii, forma corecta, alternative | Todo | P1 | 1z | V1 | Integrare DeepSeek API · Exercise library | —
30 | Tips accidentari | Sfaturi pentru recuperare accidentari comune | Todo | P2 | 1z | V1 | Integrare DeepSeek API | —
31 | UI Chat screen | Ecran chat simplu, mesaje succinte, max 300 chars | Todo | P1 | 2z | V1 | Integrare DeepSeek API · Caching | —
32 | AI Stress assistant | Gestionare stress bazat pe date somn + activitate | V2 | P3 | 4z | V2 | Sleep tracking · UI Chat screen | —
🌐 Social
33 | Social feed UI | Lista posturi, likes, comments conectat la backend | Partial | P0 | 3z | V1 | Auth · Create post flow | —
34 | Create post flow | Photo pick + workout attach + submit | Partial | P0 | 1z | V1 | Social feed UI | —
35 | Friends screen | Search, add, remove prieteni | Partial | P1 | 1z | V1 | Auth | —
36 | Comentarii in-app | Ecran comentarii complet cu reply + like pe comentariu | Todo | P1 | 2z | V1 | Social feed UI | —
37 | Notificari push | Like, comment, friend request — notifications_screen | Partial | P0 | 1z | V1 | Social feed UI · Friends screen | —
38 | Share pe Instagram | Share overlay card sau post ca Story/Feed | Todo | P2 | 2z | V1 | Export card ca imagine | —
39 | Share pe Facebook | Share pe Facebook | Todo | P3 | 1z | V1 | Export card ca imagine | —
🏆 Rank & Medalii
40 | Overall rank + leaderboard | Score, tier, leaderboard sezon — functional | Done | P0 |  | V1 | Start + track workout | —
41 | Rank per exercitiu | Rank specific per exercitiu — backend done | Done | P1 |  | V1 | Overall rank | —
42 | Achievements system | Badges la complete workout — backend done, UI partial | Partial | P1 | 1z | V1 | Start + track workout | —
43 | Rank per grupa musculara | Chest/legs/back rank — backend + UI | Todo | P1 | 3z | V1 | Muscle map upgrade · Rank per exercitiu | —
44 | Medalii per grupa musc. | Badge-uri vizuale per grupa, afisate in profil | Todo | P1 | 2z | V1 | Rank per grupa musculara | —
45 | Explainability rank | 'De ce ai scorul asta' + estimare next tier | Todo | P2 | 1z | V1 | Overall rank · Rank per exercitiu | —
📊 Charts & Analytics
46 | Weekly effort chart | Volum + sets + reps pe saptamana — fl_chart | Todo | P1 | 2z | V1 | Lista workouts trecute | —
47 | Monthly progress chart | Progres lunar per exercitiu principal | Todo | P1 | 2z | V1 | Weekly effort chart | —
48 | Ranking history chart | Evolutia rank-ului in timp | Todo | P2 | 1z | V1 | Overall rank + leaderboard | —
49 | Body weight chart | Grafic evolutie greutate corporala in timp | Todo | P2 | 1z | V1 | Update profil | —
50 | Yearly overview | An complet: activitate, volum, streaks | Todo | P2 | 2z | V1 | Activity calendar · Weekly effort chart | —
🥗 Nutritie
51 | Nutritie backend | POST /v1/nutrition/log, GET /v1/nutrition/today | Todo | P1 | 2z | V1 | Auth · DB schema | —
52 | Food search SQLite | Cauta aliment din foods.db local | Partial | P1 | 2z | V1 | Nutritie backend | —
53 | Log masa zilnica | Adauga aliment + cantitate + masa (B/L/D) | Partial | P1 | 2z | V1 | Food search SQLite · Nutritie backend | —
54 | Macro tracking zilnic | Afisare calorii + P/C/F per zi cu grafic | Todo | P1 | 2z | V1 | Log masa zilnica | —
55 | Nutritie UI end-to-end | Ecran complet functional, conectat la backend | Todo | P1 | 3z | V1 | Macro tracking · Log masa · Food search | —
💤 Sleep & Wellness
56 | Sleep tracking | Integrare Health API iOS + HealthConnect Android | Todo | P2 | 3z | V1 | health package (exista deja) | —
57 | Sleep dashboard | Ore somn, calitate, grafic pe saptamana | Todo | P2 | 2z | V1 | Sleep tracking | —
58 | Motivation quotes | Quote adaptat la pattern somn + activitate zilnica | Todo | P2 | 2z | V1 | Sleep tracking · Activity calendar | —
⌚ Wearables
59 | Heart rate sync | Citire HR din wearable in timp real in workout | Todo | P2 | 3z | V1 | Start + track workout · health package | —
60 | Apple Watch UI | Complicatie sau mini-app Watch pentru workouts | Todo | P2 | 5z | V1 | Heart rate sync · Start + track workout | —
61 | Garmin/Polar/WearOS | Compatibilitate prin Health APIs | V2 | P3 | 4z | V2 | Apple Watch UI · Heart rate sync | —
🎨 Branding & UI/UX
62 | Logo final | Logo Zvelt final, vectorial, light + dark version | Todo | P0 | design | V1 | — (primul lucru de facut) | Similea
63 | Mascota BeastRise | Mascota simpla, motivationala, recognoscibila | Todo | P1 | design | V1 | Logo final | —
64 | Avatare Apple-style | Set avatare simple, clean, personalizabile | Todo | P1 | design | V1 | Logo final (style guide) | —
65 | Dark theme consistent | Orange #FC4C02 accent, dark bg, consistent | Partial | P0 | 2z | V1 | Logo final | —
66 | Micro-animatii | Transitions, loading states, feedback vizual | Todo | P1 | 3z | V1 | Social feed UI · Nutritie UI · Profile | —
67 | Onboarding redesign | Flow mai atractiv, modern, cu mascota integrata | Todo | P2 | 2z | V1 | Mascota BeastRise · Avatar upgrade | —
68 | App Store assets | Screenshots, preview video, descriere, keywords | Todo | P0 | 2z | V1 | Dark theme · Micro-animatii · App functional | —
69 | Google Play assets | Assets adaptate pentru Play Store | Todo | P0 | 1z | V1 | App Store assets | —
LEGENDA — Status: Done · Partial · Todo · V2 ¦ In progres de: Similea / Ciprian / Amandoi ¦ Dependente = ce trebuie finalizat inainte